## Risk Assessment
DRA Field Operations Risk Assessment: UPPER HUNTER VALLEY (OP TRAILL). Rev: 17/2/2022
| SCOPE: | DRA Field Operation recovery activities to support flood disaster community. Dates: 24 Feb to 26 Mar 2022. Four Waves each working 7 x 14hour days. Hand tools and powered mobile plant in use. Location: Upper Hunter Valley. FOB at: Coolah
RISK MATRIX
Filter | Item | Hazard | Potential Outcome | Consequence | Likelihood | Raw Risk | Risk Treatment | Current controls | Additional DRA controls required | Residual risk | Responsibility | Due date | Date Completed | Remarks for this Operation
| 1 | Enterprise Risk - Legal - serious injury or repeated notifiable breach | Prosecution for HS event: Fine, loss of reputation, insurance impacted | Major | possible | Critical | Retain | Quality and application of SMS. Identified High Risks and SWMS for them | Incident reporting to learn and improve. Implement HS culture improvements | Moderate | COO, SMS, All
| 2 | Enterprise Risk - Reputational - Damage or failure in service to community | Community complaint: impacts funding and repeat work. Insurance increase | Serious | Possible | High | Retain | Pre-Ops and Ops planning and controls. Deployment screening... Competency. | Awareness. Review and assurance processes | Moderate | Mobilisation, Planning
| 3 | Enterprise Risk - Financial - Competition, limitation of funding | Inhibited operations, delays, scope limitation, retention | Serious | Possible | High | Retain | Marketing strategy. PRO delivery. Funding focus. Reporting. | ERM process, review and assurance linked to PRO and Marketing | Moderate | Marcoms
| 4 | Enterprise Risk - Financial. Withdrawl of funding, lost sponsor | Inhibited operations, delays, scope limitation, retention | Serious | Possible | High | Retain | Appraisal & Reporting. Marketing strategy | Awareness. Review and assurance processes | Moderate | COO, Marcoms, PRO, All
| 5 | Pre-Ops Assessment Risks - HS incident, failure of DA, Loss | Injury, Inadequate DA, Consequential impacts | Serious | Possible | High | Retain | Competent assessors, Risk Assessment, Planning, SWMS's for High Risks | Awareness. Conduct pre-visit Risk Assessment | Low | Field Ops , Logistics, Planners
| 6 | Equipment and Plant Operators have training but insufficient practice of required skills. | Injury, Damage to property and Equipment. Discredit DRA in eyes of clients who have higher competencies. Consequent damage to DRA organisation objectives | Major | Possible | Critical | Retain | EOI Screening before Deployment. SWMS for High Risks Review of VOCs. Mentor / buddy. Day to Day monitoring including Briefing and de-briefing sessions. | Early identification of required plant and operators. Grading of tasks to match capabilities. Use of mentor at Field Operation. Ongoing Risk Assessment. Attention of STL and SO for focus. Conduct of VoC of plant and equipment for each wave | High | Mobilisation, Mission Commanders and STL
| 7 | Operating in remote areas where emergency management is challenging | Response and time to medical support is life threatening for serious events | Major | Possible | Critical | Retain | EOI Screening before Deployment. SWMS for High Risks Review of VOCs. Medical foresight and advice | Specific measures required against possible scenarios Deploy satellite comms including Inreach and phones. | High | Mobilisation, Planning. Mission Commanders &STL
| 8 | Electrical safety (including hand tools, contact with overhead wires and damaged infrastructure) | Serious injury or death | Major | Likely | Critical | Retain | SWMS: - Electrical Safety - Powered Hand Tools - Powered Mobile Plant Test and Tag inspection? | * Power tools are in test date * Employment of RCD devices in FOB and when using powered tools * Compliance with tree felling procedures (if undertaken) * Compliance with safe operation of mobile plant * Isolation of power when in hazardous environments | Moderate | Mission Commanders and STL
| 9 | Falling objects (including deadfall) | Serious injury or death | Major | Possible | High | Retain | SWMS: - Workiing at Heights - Powered Mobile Plant | * Inclusion of potential hazards in site safety assessment/ Safety 5 * establishment of exclusion zones * mandate wearing of helmets * use of spotter when using mobile plant and if tree felling. * mobile plant to have falling object protection (FOPS) | Moderate | Mission Commanders and STL
| 10 | Demolition | Serious injury or death | Major | Possible | High | Avoid | Removed from permissable DRA activities | SWMS: Demolition and Debris Removal | High |  |  |  | DRA is not to undertake demolition of structures over 2 metres (? where is this recorded? (DL)
| 11 | Fatigue | Serious injury or death | Major | Possible | High | Retain | SWMS: -Fatigue Management - Driving Vehicles EOI screening before deployment | * MC and STL monitor health and well-being during deployed operations * MC to ensure adequate time and facilities for rest in accordance with environmental conditions * MC to monitor personal travel plans * MC to ensure adequate provision for rest stops and relief drivers during deployment and redeployment * Operation of TRA buses and other heavy vehicles in accordance with Heavy Vehicle National Law. (HVNL) * Implement controls in relevant SWMS * MC is to ensure completion of driver authorisations | Moderate | Mission Commanders and STL |  |  | Driver Authorisation Form
| 12 | Mobile Plant (incl excavators and bobcats/forklifts) | Serious injury or death | Major | Possible | High | Retain | SWMS: -Powered Mobile Plant - Fatigue Management EOI & VOC Screening before deployment. VOC records of training. | * Ensure the competence of DRA operators * Introduce L1 and L2 work capability depending on operator competence * Ensure currency of any licensing requirement eg forklifts * Ensure the serviceability of mobile plant including safety features and operational controls * Ensure the conduct of site-specific risk assessments requiring the use of mobile plant * Ensure the conduct of pre-start checks and maintenance, and adherence to SWMS * Ensure the maintenance of operator and equipment records * Ensure compliance with the operators manual * Ensure the use of spotters and exclusion zones * Monitor operator fatigue | Moderate | Mission Commanders and STL
| 13 | Intermediate and advanced Tree felling | Serious injury or death | Major | Likely | Extreme | Avoid | SWMS: - Chainsaw Trim and Cut Felled Trees Basic and Intermediate Felling. Equipment Manuals Essential: * DRA members complete Level 3 and Level 4 tree felling courses | * Ensure the competence of DRA operators including the conduct of Verification of Competency. * Ensure the serviceability of equipment including safety features and operational controls * Ensure the conduct of site-specific risk assessments requiring the use of this equipment * Ensure the conduct of pre-start checks and maintenance, and adherence to SWMS * Ensure the maintenance of operator and equipment records * Ensure compliance with the operators manual * Ensure the use of spotters and exclusion zones * Monitor operator fatigue | Moderate | Mission Commanders, and STL
| 14 | Cross cutting and basic tree felling | Serious injury | Major | Possible | High | Retain | SWMS: - Chainsaw Trim and Cut Felled Trees, Basic and intermediate felling. Equipment Manuals Essential: * Conduct Level 1 chainsaw training * Conduct Level 2 chainsaw training | * Ensure the competence of DRA operators * Ensure the serviceability of equipment including safety features and operational controls * Ensure the conduct of site-specific risk assessments requiring the use of this equipment * Ensure the conduct of pre-start checks and maintenance, and adherence to SWMS * Ensure the maintenance of operator and equipment records * Ensure compliance with the operators manual * Ensure the use of spotters and exclusion zones * Monitor operator fatigue | Moderate | Mission Commanders and STL
| 15 | Working at Heights | Serious injury or death | Substantial | Possible | High | Retain | SWMS: -Working at Heights | * DRA personnel are not to undertake tasks which require working at heights without the specific approval of NDFO * Conduct a risk assessment for the establishment of the agreed task -Safety 5 * Establish and maintain appropriate equipment (including safety equipment) to support the prescribed role * Establish and maintain appropriate safety equipment | Moderate | Mission Commanders and STL
| 16 | Site contaminants | Serious illness or death | Major | Possible | High | Retain | SWMS: -Site Contaminants -Demoition and Debris Removal | *DA team and ST to conduct site inspection/risk assessment to detect the presence of contaminants or potentially hazardous chemicals * Teams to engage with owner/occupier to identify hazardous chemicals * IMT/safety officer to source Safety Data Sheet and seek advice as necessary * PPE to be worn as prescribed | Moderate | Mission Commanders, STL National Safety Manager
| 17 | Asbestos | Serious illness or death | Major | Likely | Critical | Avoid | SWMS: -Site Contaminants -Demoition and Debris Removal Request asbestos detail from Council as part of DA Notify owner / council of inadvertant exposure | * DRA to evaluate Asbestos training and develop procedures for inadvertent exposure to asbestos | High | National Safety Manager
| 19 | Pathogens including COVID | Serious illness, potentail death. Long term health impact | Serious | Possible | High | Avoid Retain | Refer To Covid Risk Assessment, and DRA Covid-19 Operations Safety Plan. Extract requirements to be emphasised in OpOrd. DRA Mandates Vaccinations to meet Federal Governement Advice before Deployment | * Test Covid prevelence in location. * provide facilities for segregation and isolation. * Locate approved testing clinic * DRA Covid Working Group and NMM to monitor current COVID situation | Moderate | Mission Commander/ Team Leader
| 20 | Vehicle safety, driving and travel - Include remote country roads in poor condition or unknown to driver. Outside of Emergency / mobile phone coverage | Serious injury or death | Major | Possible | High | Retain | SWMS: - Driving Vehicles - Fatigue Management * DRA license register | * members required to declare loss of license or significant infringements * members driving DRA vehicles to be paired and share driving * deployment and redeployment planning to consider fatigue management * members encouraged to car pool when driving own means *Members required to demonstrate off-road competence * Members are to complete the DRA Driver Authorisation | Moderate | Mission Comanders, Logistics |  |  | Issue sat phones for emergency use on site or in transit. An accident in some places may be >1hr from appropriate medical help as Coolah District Hospital (in AO) and Merriwa District Hospital (80km from Coolah) may be of limited assistance. Nearest major facility is John Hunter Hospital in Newcastle. Westpac AW139 rescue helicopter (based in Newcastle) cruising speed is 260km/hr (135 knots). Newcastle to Coolah approx. 250km direct.
| 21 | Small plant including chainsaws | Serious injury | Serious | Likely | High | Retain | SWMS: - Chainsaw Trim and Cut Felled Trees Basic and Intermediate Felling. - Hazardous Manual Tasks. - Powered Hand Tools * Equipment Manuals and Regisers EOI Screeing before deployment | * Plant is to be maintained in accordance with manufacturers' instructions * DRA is to maintain a log book for each item of plant * Plant is to be repaired by accredited providers * Only genuine spare parts are to be utilised * Plant is only to be operated by personnel who demonstrate their competence and are rauthorised by DRA * Members are to complete Verification of Competency where available | Moderate | Mission Commanders
| 22 | Local environemnt - fauna - venomous snake-bite, insect bite. Bee sting | Serious illness, potential fatality | Major | Possible | Critical | Retain | STL Competency. Screening EOIs before deployment * First aid training for all volunteers. * Snake bite kits * All workers long sleeves, boots and trousers. | Daily / ongoing Risk Assessment. * Awareness of risk - SOs briefing. * Carriage of snakebite kits with STs. * Refresher training in snakebite first aid. * Utilise snake gaiters | High | Mission Commanders & STL
| 23 | Local environemnt - poisonous flora - e.g. hemlock | Moderate to severe allergic reaction - serious illness to death There is also a risk of spreading it across the area. | Medium | Possible | Moderate | Retain | Identify from local DA and authorities. Involve Biosecurity to understand measures required | * identify allegic reaction potential when screening for deployment * Awareness of risk - SOs briefing. * Provide datasheet and sample for volunteers to learn to identify. * Provide briefing on signs and symptoms and first aid actions. | Low | Mission Commanders |  |  | References for Look up: https://weeds.dpi.nsw.gov.au/Weeds/Hemlock https://www.healthline.com/health/hemlock-poisoning
| 24 | Local environment - weather - higher altitude - rapid changes in weather - rain, wind, lightning. | Hypothermia. | Serious | Possible | High | Retain | SWMS: - Extremes of weather. | * Awareness of risk - SOs briefing. * Members to take wet and cold weather clothing to sites. * STL to monitor weather and make decision as to continuation of work as situation evolves. | Moderate | Mission Commanders
Note on J11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: VOC Reply: agreed
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: satellite comms Reply: agreed
Note on J13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should "implement controls in relevant SWMS" not be a CURRENT control, rather than an ADDITIONAL control? Reply: agreed and removed
Note on J16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove and amend the hyperlink Reply: agreed, but not able to edit out Reply: Link removed, see column O
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I dont think we have any advanced tree fellers yet. There is no SWMS for advanced felling, but see the protocol Reply: Retained from template for future potential
Note on I22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I don't believe it should be our control to engage specialist services to remove asbestos. Ours should be to: - request asbestos detail for properties from Council as part of DA process (and attend only properties recorded as clear) - notify owner / council if we have inadvertent exposure Reply: Yes, changed as you suggested.
Note on J24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: amend the hyperlink to MS Reply: Removed
Note on O24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dixon Lowe Please see further detail in the ORT report
Note on J26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: snake gaiters Reply: Thanks,

## Instructions
Instructions for the use of this Field Operations Risk Assessment
1 | This is a document that could be used as evidence to demonstrate how DRA have managed the risks of a particular operation..
2 | It is structured for ongoing Field Operation support, Recording foreseable hazards, risk assessment and controls used.
3 | The following is required for each field operation:
| a. | Completion of the Scope of Operational activities.- outlines what Health and Safety must cover..
| b. | Review of all Hazards listed and confirming all foreseeable hazards are covered for this operation.
| c. | If a hazard is not covered, firstly see if it could fit under an existing Hazard, or that a new Hazard is required to be added. Note that the creation of new hazard entries (Rows) will be checked by NSM for agreement that the entry is appropriate.
| d. | Read the controls columns carefully for application in this Operation. Add improvements / updates as necessary.
| e. | Use the remarks columns to specify conditions applicable to this Operation
The above retains the integrity of the Risk Assessments for ongoing DRA use whilst exceptional conditions are in the Remarks column
4 | In using the Risk Assessment, please understand:
Raw Risks are without controls - don't do the human ting of assuming controls
Residual Risks are with controls - consider the pragmatic implementation and adequacy in DRA operations
Residual Risks determine the priority for attention (that means discussion and acceptance by leadership
Whatever the Risk Assessment produces is OWNED by leadership
5 | Concerns and improvements
This is a living document - it has to be used and the more users the safer we are - ENGAGEMENT is key to that success
If you have concerns or offer improvements please contact NSM or your DRT Safety Coordinator